## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2245-SWEN-261-04-3c-A New Page
Testing Team Name | 2245-SWEN-261-04-5e-Iwanttogohome

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
Account Creation | GIVEN I am not signed in WHEN I provide valid username, password, and select a role THEN my account is created and I am redirected to dashboard | Pass | OL, RL, AN, DS: Successfully logged in
Login + Authentication | GIVEN correct credentials WHEN I login THEN I am redirected to dashboard | Pass | OL, RL, AN, DS: Successfully logged in
Login + Authentication | GIVEN incorrect credentials WHEN I login THEN error message shown and remain logged out | Pass | OL, RL, AN, DS: Success
Logout | GIVEN I am logged in WHEN I click logout THEN my session ends and I am redirected to the home page | Pass | OL, RL, AN, DS: Success
Permissions Management | GIVEN I am an Admin WHEN I view user roles THEN I see a list of all users with roles |  | Not yet implemented
Permissions Management | GIVEN I am an Admin WHEN I change a user’s role THEN the role updates immediately |  | Not yet implemented
Viewing Available Books in Cart | GIVEN I am a helper WHEN I open my cart THEN I see a list of all books currently added | Pass | OL, RL, AN, DS: Success
Adding Books to Funding Basket | GIVEN I am a helper WHEN I add a book to my funding basket THEN the book appears in my basket | Pass | OL, RL, AN, DS: Success
Checkout & Payment | GIVEN user is a Helper and checks out THEN total price displays and they’re prompted for billing info | Pass | OL, RL, AN, DS: Success
Checkout & Payment | GIVEN valid billing info THEN books are removed from cupboard |  | Not yet implemented
Checkout & Payment | GIVEN invalid billing info THEN checkout is blocked |  | Not yet implemented
Search for Books | GIVEN multiple books exist WHEN I search by partial name THEN the system returns relevant books | Pass | OL, RL, AN, DS: Success
Update Books | GIVEN a book exists WHEN I update its details THEN the cupboard reflects the updated information | Pass | OL, RL, AN, DS: Success
Get Entire Cupboard | GIVEN multiple books exist WHEN I request all books THEN the system returns a list of all books in the cupboard | Pass | OL, RL, AN, DS: Success
Get a Single Book | GIVEN a book exists WHEN I request that book by name or ID THEN the system returns the full details of that book | Pass | OL, RL, AN, DS: Success
Delete a Single Book | GIVEN the book exists WHEN I request deletion THEN the book is removed from the cupboard | Pass | OL, RL, AN, DS: Success
Approved Books Storage | GIVEN no existing book name WHEN I submit a book object THEN the book is created, saved, and returned with a 201 status |  | Not yet implemented
Approved Books Storage | GIVEN approval from request pool THEN the book is added to the cupboard |  | Not yet implemented
Approved Books Storage | GIVEN funded/shipped book THEN the book is removed from the cupboard |  | Not yet implemented
Requesting a Book (ENHANCEMENT) | GIVEN an inmate requests a book WHEN the request is submitted THEN it appears in the request pool | Pass | OL, RL, AN, DS: Success
Admin Approving Requests (ENHANCEMENT) | GIVEN an Admin views the request pool WHEN they approve a request THEN the book is moved to the cupboard | Pass | OL, RL, AN, DS: Success
Notification when Book is Approved or Denied | GIVEN an inmate’s request is reviewed WHEN it is approved or denied THEN the inmate receives a notification |  | Not yet implemented
Notification when Book is Funded | GIVEN an inmate’s request is approved and in the cupboard WHEN a helper funds the book THEN the inmate receives a “funded” notification |  | Not yet implemented
Book Shipment | GIVEN an inmate WHEN a helper purchases a book THEN the inmate receives a “shipped” notification |  | Not yet implemented
Book Shipment | GIVEN a notification THEN the inmate may send a thank-you note |  | Not yet implemented
Book Request Limit (ENHANCEMENT) | GIVEN an inmate WHEN they reach their request limit THEN they cannot request additional books | Pass | OL, RL, AN, DS: Success
Request Pool Management | GIVEN an Admin WHEN they access the request pool THEN they can see, approve, or deny book requests | Pass | OL, RL, AN, DS: Success
Prison Code Management (ENHANCEMENT) | GIVEN an Admin WHEN they create a prison code THEN it is stored and validated for future use | Pass | OL, RL, AN, DS: Success
Prison Code Management (ENHANCEMENT) | GIVEN an Admin WHEN they update a prison code THEN the updated details are saved | Pass | OL, RL, AN, DS: Success
Prison Code Management (ENHANCEMENT) | GIVEN a prisoner WHEN they register THEN their prison code is validated | Pass | OL, RL, AN, DS: Success